## Sheet1
Task ID | Due Date | Person(s) Responsible | Task | Test Plan | Dependencies
1 | 2019-04-16 | All | Test and characterize components | Test each component and characterize the inputs and outputs | Receiving components | Done | Behind | In Progress | High Level
1a |  | Joe | Test PIR motion sensor | Use Digilent Analog Discovery2 power supply functionality to supply 3.3V to the power pins. Connect the output pin to the Digilent voltmeter and wave a hand in front of the sensor. Evaluate the output voltage when the sensor is tripped. Evaluate the sensor at different distances to see whether it meets the needs of the project. Also measure input and output currents to determine what circuitry is necessary. | Receiving components
1b
1c
2 | 2019-04-18 |  | Build circuit on a breadboard | Build circuit on a breadboard and verify that it functions as expected.
2a |  |  | Build a basic circuit to test output of PIR motion sensor | Put PIR sensor on breadboard and test the output values to ensure wiring works | 1a
2b
2c
3 | 2019-04-18 |  | Connect breadboard circuit to controller | Test interaction between controller and circuit by using the controller to read inputs and drive outputs.
3a |  |  | Connect PIR circuit to controller | Read values sent by the PIR when it is triggered | 2a ,5a
4 | 2019-04-23 |  | Build final circuitry using protoboards or other secure methods | Test circuit to verify that it works as expected in its final configuration
4a |  |  | Solder PIR circuit to protoboard | Solder and test by ensuring values outputted by the PIR still make sense | 3a
4b
4c
5 | 2019-04-25 |  | Connect final circuitry to controller | Test interaction between controller and circuit by using the controller to read inputs and drive outputs. | Task 4
5a |  |  | Connect PIR final circuit to controller | use controller to read values from the PIR motion sensor. If the value is high, then the alarm will be triggered | 4a
5b
5c
5 | 2019-04-16 |  | Develop software | Test software at every step. Testing can be performed with breadboard circuit, final circuit, or temporary circuit to simulate the hardware.
5a |  |  | poll for PIR high output | Read values from the PIR sensor using a while loop to determine when exactly the alarm is triggered | 1a
5b |  |  | Receiving and Transmitting texts (BBBw) | utilize C and python to send and receive text messages using a cell phone
5c |  |  | Develop code for disabling alarm system | Code will be made so the BBBw will be able to receive a text from the user's phone and use the combination the user sends to disable the alarm system | 5b
5d |  |  | Develop code for outputting alarm through speaker | Use system() commands to have mp3 files play through a speaker connected to the BBBw with USB connection | 5c*
5e
6 | 2019-04-25 |  | Integrate final hardware and software | Test the entire system and verify operation | Task 4, 5
6a |  |  | Download mp3 playing software to BBBw | Integrate into the BBBw so we can play any mp3 file as an audio output to a speaker
6b |  |  | Connect the entire circuit and test | Be able to enable and disable the alarm system with text messages, and have text messages be sent to the user if the alarm is triggered | 5
7 | 2019-04-25 |  | Build case/packaging/platform for the system | Ensure that all pieces fit and are secured
7a |  |  | 3d print case | Make a case large enough to have the BBBw, protoboard, speaker, and PIR sensor to all comfortably and securely sit inside | 6
7b
7c
7d